## PMBOK 6
S No | Knowledge Area | Process | Process Group | Inputs | Tools & Techniques | Outputs
1 | Integration Management | Develop Project charter | Initiating | Business Documents | Expert Judgment | Project charter
2 | Integration Management | Develop Project charter | Initiating | Agreements | Data gathering | Assumption log
3 | Integration Management | Develop Project charter | Initiating | Enterprise Environmental Factors | Interpersonal and team skills
4 | Integration Management | Develop Project charter | Initiating | Organizational Process Assets | Meetings
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 4-2, Page 75
5 | Integration Management | Develop Project management plan | Planning | Project charter | Expert Judgment | Project Management Plan
6 | Integration Management | Develop Project management plan | Planning | Outputs from Other Processes | Data gathering
7 | Integration Management | Develop Project management plan | Planning | Enterprise Environmental Factors | Interpersonal and team skills
8 | Integration Management | Develop Project management plan | Planning | Organizational Process Assets | Meetings
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 4-4, Page 82.
9 | Integration Management | Direct and Manage Project Work | Executing | Project Management Plan | Expert Judgment | Deliverables
10 | Integration Management | Direct and Manage Project Work | Executing | Project Documents | Project Mgmt Information System | Work Performance Data
11 | Integration Management | Direct and Manage Project Work | Executing | Approved Change Requests | Meetings | Issue log
12 | Integration Management | Direct and Manage Project Work | Executing | Enterprise Environmental Factors |  | Change Requests
13 | Integration Management | Direct and Manage Project Work | Executing | Organizational Process Assets |  | Project Management Plan updates
14 | Integration Management | Direct and Manage Project Work | Executing |  |  | Project Documents updates
15 | Integration Management | Direct and Manage Project Work | Executing |  |  | Organizational Process Assets updates
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 4-6, Page 90.
16 | Integration Management | Manage Project Knowlege | Executing | Project Management Plan | Expert Judgment | Lessons learned register
17 | Integration Management | Manage Project Knowlege | Executing | Project Documents | Knowledge management | Project Management Plan updates
18 | Integration Management | Manage Project Knowlege | Executing | Deliverables | Information management | Organizational Process Assets updates
19 | Integration Management | Manage Project Knowlege | Executing | Enterprise Environmental Factors | Interpersonal and team skills
20 | Integration Management | Manage Project Knowlege | Executing | Organizational Process Assets
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 4-8, Page 98.
21 | Integration Management | Monitor and Control Project Work | M&C | Project Management Plan | Expert Judgment | Work Performance Reports
22 | Integration Management | Monitor and Control Project Work | M&C | Project documents | Data analysis | Change Requests
23 | Integration Management | Monitor and Control Project Work | M&C | Work Performance Information | Decision making | Project Management Plan updates
24 | Integration Management | Monitor and Control Project Work | M&C | Agreements | Meetings | Project Documents updates
25 | Integration Management | Monitor and Control Project Work | M&C | Enterprise Environmental Factors
26 | Integration Management | Monitor and Control Project Work | M&C | Organizational Process Assets
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 4-10, Page 105.
27 | Integration Management | Perform Integrated Change Control | M&C | Project Management Plan | Expert Judgment | Approved change requests
28 | Integration Management | Perform Integrated Change Control | M&C | Project documents | Data analysis | Project Management plan updates
29 | Integration Management | Perform Integrated Change Control | M&C | Work Performance Reports | Data analysis | Project documents updates
30 | Integration Management | Perform Integrated Change Control | M&C | Change Requests | Decision making
31 | Integration Management | Perform Integrated Change Control | M&C | Enterprise Environmental Factors | Meetings
32 | Integration Management | Perform Integrated Change Control | M&C | Organizational Process Assets
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 4-12, Page 113.
33 | Integration Management | Close Project or Phase | Closing | Project charter | Expert Judgment | Project Documents updates
34 | Integration Management | Close Project or Phase | Closing | Project Management Plan | Data analysis | Final Product, services or result transition
35 | Integration Management | Close Project or Phase | Closing | Project Documents | Meetings | Final Report
36 | Integration Management | Close Project or Phase | Closing | Accepted Deliverables |  | Organizational Process Assets updates
37 | Integration Management | Close Project or Phase | Closing | Business Documents
38 | Integration Management | Close Project or Phase | Closing | Agreements
39 | Integration Management | Close Project or Phase | Closing | Procurement documentation
40 | Integration Management | Close Project or Phase | Closing | Organizational Process Assets
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 4-14, Page 121.
| Knowledge Area | Process | Process Group | Inputs | Tools & Techniques | Outputs
41 | Scope: | Plan Scope Management | Planning | Project charter | Expert Judgement | Scope Management Plan
42 | Scope: | Plan Scope Management | Planning | Project Management Plan | Data analysis | Requirements Management Plan
43 | Scope: | Plan Scope Management | Planning | Enterprise Environmental Factors | Meetings
44 | Scope: | Plan Scope Management | Planning | Organizational Process Assets
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 5-2, Page 134.
45 | Scope: | Collect Requirements | Planning | Project Charter | Expert Judgement | Requirements Documentation
46 | Scope: | Collect Requirements | Planning | Project Management Plan | Data Gathering | Requirements Traceability Matrix
47 | Scope: | Collect Requirements | Planning | Project Documents | Data analysis
48 | Scope: | Collect Requirements | Planning | Business Documents | Decision making
49 | Scope: | Collect Requirements | Planning | Agreements | Data Representation
50 | Scope: | Collect Requirements | Planning | Enterprise Environmental Factors | Interpersonal and team skills
51 | Scope: | Collect Requirements | Planning | Organizational Process Assets | Context Diagram
52 | Scope: | Collect Requirements | Planning |  | Prototypes
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 5-4, Page 138.
53 | Scope: | Define Scope | Planning | Project charter | Expert Judgment | Project Scope Statement
54 | Scope: | Define Scope | Planning | Project Management Plan | Data analysis | Project Documents updates
55 | Scope: | Define Scope | Planning | Project Documents | Decision making
56 | Scope: | Define Scope | Planning | Enterprise Environmental Factors | Interpersonal and team skills
57 | Scope: | Define Scope | Planning | Organizational Process Assets | Product Analysis
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 5-8, Page 150.
58 | Scope: | Create WBS | Planning | Project Management Plan | Expert Judgement | Scope Baseline
59 | Scope: | Create WBS | Planning | Project Documents | Decomposition | Project Documents updates
60 | Scope: | Create WBS | Planning | Enterprise Environmental Factors
61 | Scope: | Create WBS | Planning | Organizational Process Assets
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 5-10, Page 156.
62 | Scope: | Validate Scope | M&C | Project Management Plan | Inspection | Accepted Deliverables
63 | Scope: | Validate Scope | M&C | Project Documents | Decision Making | Work Performance Information
64 | Scope: | Validate Scope | M&C | Verified Deliverables |  | Change Requests
65 | Scope: | Validate Scope | M&C | Work Performance Data |  | Project Documents Updates
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 5-15, Page 163.
66 | Scope: | Control Scope | M&C | Project Management Plan | Data Analysis | Work Performance Information
67 | Scope: | Control Scope | M&C | Project Documents |  | Change Requests
68 | Scope: | Control Scope | M&C | Work Performance Data |  | Project Management Plan Updates
69 | Scope: | Control Scope | M&C | Organizational Process Assets |  | Project Documents Updates
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 5-17, Page 167.
| Knowledge Area | Process | Process Group | Inputs | Tools & Techniques | Outputs
70 | Schedule Management | Plan Schedule Management | Planning | Project charter | Expert Judgement | Schedule Management Plan
71 | Schedule Management | Plan Schedule Management | Planning | Project Management Plan | Data Analysis
72 | Schedule Management | Plan Schedule Management | Planning | Enterprise Environmental Factors | Meetings
73 | Schedule Management | Plan Schedule Management | Planning | Organizational Process Assets
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 6-3, Page 179.
74 | Schedule Management | Define Activities | Planning | Project Management Plan | Expert Judgment | Activity List
75 | Schedule Management | Define Activities | Planning | Enterprise Environmental Factors | Decomposition | Activity Attributes
76 | Schedule Management | Define Activities | Planning | Organizational Process Assets | Rolling Wave Planning | Milestone List
77 | Schedule Management | Define Activities | Planning |  | Meetings | Change Requests
78 | Schedule Management | Define Activities | Planning |  |  | Project Management Plan Updates
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 6-5, Page 183.
79 | Schedule Management | Sequence Activities | Planning | Project Management Plan | Precedence Diagramming Method (PDM) | Project Schedule Network Diagrams
80 | Schedule Management | Sequence Activities | Planning | Project Documents | Dependency Determination and Integration | Project Documents Updates
81 | Schedule Management | Sequence Activities | Planning | Enterprise Environmental Factors | Leads & Lags
82 | Schedule Management | Sequence Activities | Planning | Organizational Process Assets | Project Management Information System
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 6-7, Page 187.
83 | Schedule Management | Estimate Activity Durations | Planning | Project Management Plan | Expert Judgment | Duration Estimates
84 | Schedule Management | Estimate Activity Durations | Planning | Project Documents | Analogous Estimating | Basis of Estimates
85 | Schedule Management | Estimate Activity Durations | Planning | Enterprise Environmental Factors | Parametric Estimating | Project Documents Updates
86 | Schedule Management | Estimate Activity Durations | Planning | Organizational Process Assets | Three-Point Estimating
87 | Schedule Management | Estimate Activity Durations | Planning |  | Bottom-Up Estimating
88 | Schedule Management | Estimate Activity Durations | Planning |  | Data Analysis
89 | Schedule Management | Estimate Activity Durations | Planning |  | Decision Making
90 | Schedule Management | Estimate Activity Durations | Planning |  | Meetings
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 6-12, Page 195.
91 | Schedule Management | Develop Schedule | Planning | Project Management Plan | Schedule Network Analysis | Schedule Baseline
92 | Schedule Management | Develop Schedule | Planning | Project Documents | Critical Path Method | Project Schedule
93 | Schedule Management | Develop Schedule | Planning | Agreements | Resource Optimization | Schedule Data
94 | Schedule Management | Develop Schedule | Planning | Enterprise Environmental Factors | Data Analysis | Project calendars
95 | Schedule Management | Develop Schedule | Planning | Organizational Process Assets | Leads and Lags | Change Requests
96 | Schedule Management | Develop Schedule | Planning |  | Schedule Compression | Project Management Plan Updates
97 | Schedule Management | Develop Schedule | Planning |  | Project Management Information System | Project Documents Updates
98 | Schedule Management | Develop Schedule | Planning |  | Agile Release Planning
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 6-14, Page 205.
99 | Schedule Management | Control Schedule | M&C | Project Management Plan | Data Analysis | Work Performance Information
100 | Schedule Management | Control Schedule | M&C | Project Documents | Critical Path Method | Schedule Forecasts
101 | Schedule Management | Control Schedule | M&C | Work Performance Data | Project Management Information System | Change Requests
102 | Schedule Management | Control Schedule | M&C | Organizational Process Assets | Resource Optimization | Project Management Plan Updates
103 | Schedule Management | Control Schedule | M&C |  | Leads and Lags | Project Documents Updates
104 | Schedule Management | Control Schedule | M&C |  | Schedule Compression
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 6-22, Page 222.
| Knowledge Area | Process | Process Group | Inputs | Tools & Techniques | Outputs
105 | Cost Management: | Plan Cost Management | Planning | Project charter | Expert Judgement | Cost Management Plan
106 | Cost Management: | Plan Cost Management | Planning | Project Management Plan | Data Analysis
107 | Cost Management: | Plan Cost Management | Planning | Enterprise Environmental Factors | Meetings
108 | Cost Management: | Plan Cost Management | Planning | Organizational Process Assets
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 7-2, Page 235.
109 | Cost Management: | Estimate Costs | Planning | Project Management Plan | Expert Judgment | Cost Estimates
110 | Cost Management: | Estimate Costs | Planning | Project Documents | Analogous Estimating | Basis of Estimates
111 | Cost Management: | Estimate Costs | Planning | Enterprise Environmental Factors | Parametric Estimating | Project Documents Updates
112 | Cost Management: | Estimate Costs | Planning | Organizational Process Assets | Bottom-up Estimating
113 | Cost Management: | Estimate Costs | Planning |  | Three-Point Estimating
114 | Cost Management: | Estimate Costs | Planning |  | Data Analysis
115 | Cost Management: | Estimate Costs | Planning |  | Project Management Information System
116 | Cost Management: | Estimate Costs | Planning |  | Decision Making
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 7-4, Page 240.
117 | Cost Management: | Determine Budget | Planning | Project Management Plan | Expert Judgement | Cost Baseline
118 | Cost Management: | Determine Budget | Planning | Project Documents | Cost Aggregation | Project Funding Requirements
119 | Cost Management: | Determine Budget | Planning | Business Documents | Data Analysis | Project Documenst Updates
120 | Cost Management: | Determine Budget | Planning | Agreements | Historical Information Review
121 | Cost Management: | Determine Budget | Planning | Enterprise Environmental Factors | Fund Limit Reconciliation
122 | Cost Management: | Determine Budget | Planning | Organizational Process Assets | Financing
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 7-6, Page 248.
123 | Cost Management: | Control Costs | M&C | Project Management Plan | Expert Judgment | Work Performance Information
124 | Cost Management: | Control Costs | M&C | Project Documents | Data Analysis | Cost Forecasts
125 | Cost Management: | Control Costs | M&C | Project Funding Requirements | To-Complete Performance Index (TCPI) | Change Requests
126 | Cost Management: | Control Costs | M&C | Work Performance Data | Project Management Information System | Project Management Plan Updates
127 | Cost Management: | Control Costs | M&C | Organizational Process Assets |  | Project Documents Updates
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 7-10, Page 257.
| Knowledge Area | Process | Process Group | Inputs | Tools & Techniques | Outputs
128 | Quality Management: | Plan Quality Management | Planning | Project Charter | Expert Judgement | Quality Management Plan
129 | Quality Management: | Plan Quality Management | Planning | Project Management Plan | Data Gathering | Quality Metrics
130 | Quality Management: | Plan Quality Management | Planning | Project Documents | Data Analysis | Project Management Plan Updates
131 | Quality Management: | Plan Quality Management | Planning | Enterprise Environmental Factors | Decision Making | Project Documents Updates
132 | Quality Management: | Plan Quality Management | Planning | Organizational Process Assets | Data Representation
133 | Quality Management: | Plan Quality Management | Planning |  | Test and Inspection Planning
134 | Quality Management: | Plan Quality Management | Planning |  | Meetings
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 8-3, Page 277.
135 | Quality Management: | Manage Quality | Executing | Project Management Plan | Data Gathering | Quality Reports
136 | Quality Management: | Manage Quality | Executing | Project Documents | Data Analysis | Test and Evaluation Documents
137 | Quality Management: | Manage Quality | Executing | Organizational Process Assets | Decision Making | Change Requests
138 | Quality Management: | Manage Quality | Executing |  | Data Representation | Project Management Plan Updates
139 | Quality Management: | Manage Quality | Executing |  | Audits | Project Documents Updates
140 | Quality Management: | Manage Quality | Executing |  | Design of X
141 | Quality Management: | Manage Quality | Executing |  | Problem Solving
142 | Quality Management: | Manage Quality | Executing |  | Qualitive Improvement Methods
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 8-7, Page 288.
143 | Quality Management: | Control Quality | M&C | Project Management Plan | Data Gathering | Quality Control Measurements
144 | Quality Management: | Control Quality | M&C | Project Documents | Data Analysis | Verified Deliverables
145 | Quality Management: | Control Quality | M&C | Approved Change Requests | Inspection | Work Performance Information
146 | Quality Management: | Control Quality | M&C | Deliverables | Testing / Product Evaluation | Change Requests
147 | Quality Management: | Control Quality | M&C | Work Performance Data | Data Representation | Project Management Plan Updates
148 | Quality Management: | Control Quality | M&C | Enterprise Environmental Factors | Meetings | Project Documents Updates
149 | Quality Management: | Control Quality | M&C | Organizational Process Assets
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 8-10, Page 298.
| Knowledge Area | Process | Process Group | Inputs | Tools & Techniques | Outputs
150 | Resources Management | Plan Resource Management | Planning | Project Charter | Expert Judgement | Resource Management Plan
151 | Resources Management | Plan Resource Management | Planning | Project Management Plan | Data Representation | Team Charter
152 | Resources Management | Plan Resource Management | Planning | Project Documents | Organizational Theory | Project Documents Updates
153 | Resources Management | Plan Resource Management | Planning | Enterprise Environmental Factors | Meetings
154 | Resources Management | Plan Resource Management | Planning | Organizational Process Assets
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 9-2, Page 312.
155 | Resources Management | Estimates Activity Resources | Planning | Project Management Plan | Expert Judgment | Resource Requirements
156 | Resources Management | Estimates Activity Resources | Planning | Project Documents | Bottom-up Estimating | Basis Of Estimates
157 | Resources Management | Estimates Activity Resources | Planning | Enterprise Environmental Factors | Analogous Estimating | Resource Breakdown Structure (RBS)
158 | Resources Management | Estimates Activity Resources | Planning | Organizational Process Assets | Parametric Estimating | Project Documents Updates
159 | Resources Management | Estimates Activity Resources | Planning |  | Data Analysis
160 | Resources Management | Estimates Activity Resources | Planning |  | Project Managemment Information System
161 | Resources Management | Estimates Activity Resources | Planning |  | Meetings
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 9-5, Page 321.
162 | Resources Management | Acquire Resources | Executing | Project Management Plan | Decision Making | Physical Resource Assignments
163 | Resources Management | Acquire Resources | Executing | Project Documents | Interpersonal and Team Skills | Project Team Assignments
164 | Resources Management | Acquire Resources | Executing | Enterprise Environmental Factors | Pre-assignment | Resource Calendars
165 | Resources Management | Acquire Resources | Executing | Organizational Process Assets | Virtual Teams | Change Requests
166 | Resources Management | Acquire Resources | Executing |  |  | Project Management Plan Updates
167 | Resources Management | Acquire Resources | Executing |  |  | Project Documents Updates
168 | Resources Management | Acquire Resources | Executing |  |  | Enterprise Environmental Factors updates
169 | Resources Management | Acquire Resources | Executing |  |  | Organizational Process Assets updates
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 9-8, Page 328.
170 | Resources Management | Develop Team | Executing | Project Management Plan | Colocation | Team Performance Assessments
171 | Resources Management | Develop Team | Executing | Project Documents | Virtual Teams | Change Requests
172 | Resources Management | Develop Team | Executing | Enterprise Environmental Factors | Communication Technology | Project Management Plan Updates
173 | Resources Management | Develop Team | Executing | Organizational Process Assets | Interpersonal and Team Skills | Project Documents Updates
174 | Resources Management | Develop Team | Executing |  | Recognition and Rewards | Enterprise Environmental Factors updates
175 | Resources Management | Develop Team | Executing |  | Training | Organizational Process Assets updates
176 | Resources Management | Develop Team | Executing |  | Individual and Team Assessments
177 | Resources Management | Develop Team | Executing |  | Meetings
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 9-10, Page 336.
178 | Resources Management | Manage Team | Executing | Project Management Plan | Interpersonal and Team Skills | Change Requests
179 | Resources Management | Manage Team | Executing | Project Documents | Project Managemment Information System | Project Management Plan Updates
180 | Resources Management | Manage Team | Executing | Work Performance Reports |  | Project Documents Updates
181 | Resources Management | Manage Team | Executing | Team Performance Assessments |  | Enterprise Environmental Factors updates
182 | Resources Management | Manage Team | Executing | Enterprise Environmental Factors
183 | Resources Management | Manage Team | Executing | Organizational Process Assets
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 9-12, Page 345.
184 | Resources Management | Control Resources | M&C | Project Management Plan | Data Analysis | Work Performance Information
185 | Resources Management | Control Resources | M&C | Project Documents | Problem Solving | Change Requests
186 | Resources Management | Control Resources | M&C | Work Performance Data | Interpersonal and Team Skills | Project Management Plan Updates
187 | Resources Management | Control Resources | M&C | Agreements | Project Managemment Information System | Project Documents Updates
188 | Resources Management | Control Resources | M&C | Organizational Process Assets
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 9-14, Page 352.
| Knowledge Area | Process | Process Group | Inputs | Tools & Techniques | Outputs
189 | Communications Management | Plan Communications Management | Planning | Project Charter | Expert Judgment | Communications Management Plan
190 | Communications Management | Plan Communications Management | Planning | Project Management Plan | Communication Requirement Analysis | Project Management Plan Updates
191 | Communications Management | Plan Communications Management | Planning | Project Documents | Communication Technology | Project Documents Updates
192 | Communications Management | Plan Communications Management | Planning | Enterprise Environmental Factors | Communication Models
193 | Communications Management | Plan Communications Management | Planning | Organizational Process Assets | Communication Methods
194 | Communications Management | Plan Communications Management | Planning |  | Interpersonal and Team Skills
195 | Communications Management | Plan Communications Management | Planning |  | Data Representation
196 | Communications Management | Plan Communications Management | Planning |  | Meetings
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 10-2, Page 366.
197 | Communications Management | Manage Communications | Executing | Project Management Plan | Communications Technology | Project Communications
198 | Communications Management | Manage Communications | Executing | Project Documents | Communication Methods | Project Management Plan Updates
199 | Communications Management | Manage Communications | Executing | Work Performance Reports | Communication Skills | Project Documents Updates
200 | Communications Management | Manage Communications | Executing | Enterprise Environmental Factors | Project Management Information system | Organizational Process Assets updates
201 | Communications Management | Manage Communications | Executing | Organizational Process Assets | Project Reporting
202 | Communications Management | Manage Communications | Executing |  | Interpersonal and Team Skills
203 | Communications Management | Manage Communications | Executing |  | Meetings
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 10-5, Page 379.
204 | Communications Management | Monitor Communications | M&C | Project Management Plan | Expert Judgement | Work Performance Information
205 | Communications Management | Monitor Communications | M&C | Project Documents | Project Management Information system | Change Requests
206 | Communications Management | Monitor Communications | M&C | Work Performance Data | Data Representation | Project Management Plan Updates
207 | Communications Management | Monitor Communications | M&C | Enterprise Environmental Factors | Interpersonal and Team Skills | Project Documents Updates
208 | Communications Management | Monitor Communications | M&C | Organizational Process Assets | Meetings
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 10-7, Page 388.
| Knowledge Area | Process | Process Group | Inputs | Tools & Techniques | Outputs
209 | Risk Management: | Plan Risk Management | Planning | Project Charter | Expert Judgement | Risk Management Plan
210 | Risk Management: | Plan Risk Management | Planning | Project Management Plan | Data Analysis
211 | Risk Management: | Plan Risk Management | Planning | Project Documents | Meetings
212 | Risk Management: | Plan Risk Management | Planning | Enterprise Environmental Factors
213 | Risk Management: | Plan Risk Management | Planning | Organizational Process Assets
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 11-2, Page 401.
214 | Risk Management: | Identify Risks | Planning | Project Management Plan | Expert Judgment | Risk Register
215 | Risk Management: | Identify Risks | Planning | Project Documents | Data Gathering | Risk Report
216 | Risk Management: | Identify Risks | Planning | Agreements | Data Analysis | Project Documents Updates
217 | Risk Management: | Identify Risks | Planning | Procurement Documentation | Interpersonal and Team Skills
218 | Risk Management: | Identify Risks | Planning | Enterprise Environmental Factors | Prompt Lists
219 | Risk Management: | Identify Risks | Planning | Organizational Process Assets | Meetings
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 11-6, Page 409.
220 | Risk Management: | Perform Qualitative Risk Analysis | Planning | Project Management Plan | Expert Judgment | Project Documents Updates
221 | Risk Management: | Perform Qualitative Risk Analysis | Planning | Project Documents | Data Gathering
222 | Risk Management: | Perform Qualitative Risk Analysis | Planning | Enterprise Environmental Factors | Data Analysis
223 | Risk Management: | Perform Qualitative Risk Analysis | Planning | Organizational Process Assets | Interpersonal and Team Skills
224 | Risk Management: | Perform Qualitative Risk Analysis | Planning |  | Risk Categorization
225 | Risk Management: | Perform Qualitative Risk Analysis | Planning |  | Data Representation
226 | Risk Management: | Perform Qualitative Risk Analysis | Planning |  | Meetings
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 11-8, Page 419.
227 | Risk Management: | Perform Quantitative Analysis | Planning | Project Management Plan | Expert Judgment | Project Documents Updates
228 | Risk Management: | Perform Quantitative Analysis | Planning | Project Documents | Data Gathering
229 | Risk Management: | Perform Quantitative Analysis | Planning | Enterprise Environmental Factors | Interpersonal and Team Skills
230 | Risk Management: | Perform Quantitative Analysis | Planning | Organizational Process Assets | Representations of uncertainty
231 | Risk Management: | Perform Quantitative Analysis | Planning |  | Data Analysis
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 11-11, Page 428.
232 | Risk Management: | Plan Risk Responses | Planning | Project Management Plan | Expert Judgment | Change Requests
233 | Risk Management: | Plan Risk Responses | Planning | Project Documents | Data Gathering | Project Management Plan Updates
234 | Risk Management: | Plan Risk Responses | Planning | Enterprise Environmental Factors | Interpersonal and Team Skills | Project Documents Updates
235 | Risk Management: | Plan Risk Responses | Planning | Organizational Process Assets | Strategies for Threats
236 | Risk Management: | Plan Risk Responses | Planning |  | Startegies for Opportunities
237 | Risk Management: | Plan Risk Responses | Planning |  | Contingent response Strategies
238 | Risk Management: | Plan Risk Responses | Planning |  | Startegies for Opportunities
239 | Risk Management: | Plan Risk Responses | Planning |  | Data Analysis
240 | Risk Management: | Plan Risk Responses | Planning |  | Decision Making
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 11-16, Page 437.
241 | Risk Management: | Implement Risk Responses | Executing | Project Management Plan | Expert Judgment | Change Requests
242 | Risk Management: | Implement Risk Responses | Executing | Project Documents | Interpersonal and Team Skills | Project Documents Updates
243 | Risk Management: | Implement Risk Responses | Executing | Organizational Process Assets | Project Management Information System
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 11-18, Page 449.
244 | Risk Management: | Monitor Risks | M&C | Project Management Plan | Data Analysis | Work Performance Information
245 | Risk Management: | Monitor Risks | M&C | Project Documents | Risk Audits | Change Requests
246 | Risk Management: | Monitor Risks | M&C | Work Performance Data | Meetings | Project Management Plan Updates
247 | Risk Management: | Monitor Risks | M&C | Work Performance Reports |  | Project Documents Updates
248 | Risk Management: | Monitor Risks | M&C |  |  | Organizational Process Assets updates
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 11-20, Page 453.
| Knowledge Area | Process | Process Group | Inputs | Tools & Techniques | Outputs
249 | Procurement Management: | Plan Procurement Management | Planning | Project Charter | Expert Judgment | Procurement Management Plan
250 | Procurement Management: | Plan Procurement Management | Planning | Business Documents | Data Gathering | Procurement Strategy
251 | Procurement Management: | Plan Procurement Management | Planning | Project Management Plan | Data Analysis | Bid Documents
252 | Procurement Management: | Plan Procurement Management | Planning | Project Documents | Source Selection Analysis | Procurement Statement of Work
253 | Procurement Management: | Plan Procurement Management | Planning | Enterprise Environmental Factors | Meetings | Source Selection Criteria
254 | Procurement Management: | Plan Procurement Management | Planning | Organizational Process Assets |  | Make-or-Buy Decision
255 | Procurement Management: | Plan Procurement Management | Planning |  |  | Independent Cost Estimates
256 | Procurement Management: | Plan Procurement Management | Planning |  |  | Change Requests
257 | Procurement Management: | Plan Procurement Management | Planning |  |  | Project Documents Updates
258 | Procurement Management: | Plan Procurement Management | Planning |  |  | Organizational Process Assets updates
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 12-2, Page 466.
259 | Procurement Management: | Conduct Procurements | Executing | Project Management Plan | Expert Judgment | Selected Sellers
260 | Procurement Management: | Conduct Procurements | Executing | Project Documents | Advertising | Agreements
261 | Procurement Management: | Conduct Procurements | Executing | Procurement Documentation | Bidder Conference | Change Requests
262 | Procurement Management: | Conduct Procurements | Executing | Seller Proposals | Data Analysis | Project Management Plan Updates
263 | Procurement Management: | Conduct Procurements | Executing | Enterprise Environmental Factors | Interpersonal and Team Skills | Project Documents Updates
264 | Procurement Management: | Conduct Procurements | Executing | Organizational Process Assets |  | Organizational Process Assets updates
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 12-4, Page 482.
265 | Procurement Management: | Control Procurements | M&C | Project Management Plan | Expert Judgment | Closed Procurements
266 | Procurement Management: | Control Procurements | M&C | Project Documents | Claims Administration | Work Performance Information
267 | Procurement Management: | Control Procurements | M&C | Agreements | Data Analysis | Procurement Documentation updates
268 | Procurement Management: | Control Procurements | M&C | Procurement Documentation | Inspection | Change Requests
269 | Procurement Management: | Control Procurements | M&C | Approved Change Requests | Audits | Project Management Plan Updates
270 | Procurement Management: | Control Procurements | M&C | Work Performance Data |  | Project Documents Updates
271 | Procurement Management: | Control Procurements | M&C | Enterprise Environmental Factors |  | Organizational Process Assets updates
272 | Procurement Management: | Control Procurements | M&C | Organizational Process Assets
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 12-6, Page 492.
| Knowledge Area | Process | Process Group | Inputs | Tools & Techniques | Outputs
273 | Stakeholder Management | Identify Stakeholders | Initiating | Project Charter | Expert Judgment | Stakeholder Register
274 | Stakeholder Management | Identify Stakeholders | Initiating | Business Documents | Data Gathering | Change Requests
275 | Stakeholder Management | Identify Stakeholders | Initiating | Project Management Plan | Data Analysis | Project Management Plan Updates
276 | Stakeholder Management | Identify Stakeholders | Initiating | Project Documents | Data Representation | Project Documents Updates
277 | Stakeholder Management | Identify Stakeholders | Initiating | Agreements | Meetings
278 | Stakeholder Management | Identify Stakeholders | Initiating | Enterprise Environmental Factors
279 | Stakeholder Management | Identify Stakeholders | Initiating | Organizational Process Assets
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 13-2, Page 507.
280 | Stakeholder Management | Plan Stakeholder Engagement | Planning | Project Charter | Expert Judgment | Stakeholder Engagement Plan
281 | Stakeholder Management | Plan Stakeholder Engagement | Planning | Project Management Plan | Data Gathering
282 | Stakeholder Management | Plan Stakeholder Engagement | Planning | Project Documents | Data Analysis
283 | Stakeholder Management | Plan Stakeholder Engagement | Planning | Agreements | Decision Making
284 | Stakeholder Management | Plan Stakeholder Engagement | Planning | Enterprise Environmental Factors | Data Representation
285 | Stakeholder Management | Plan Stakeholder Engagement | Planning | Organizational Process Assets | Meetings
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 13-4, Page 516.
286 | Stakeholder Management | Manage Stakeholder Engagement | Executing | Project Management Plan | Expert Judgment | Change Requests
287 | Stakeholder Management | Manage Stakeholder Engagement | Executing | Project Documents | Communication Skills | Project Management Plan Updates
288 | Stakeholder Management | Manage Stakeholder Engagement | Executing | Enterprise Environmental Factors | Interpersonal and Team Skills | Project Documents Updates
289 | Stakeholder Management | Manage Stakeholder Engagement | Executing | Organizational Process Assets | Ground Rules
290 | Stakeholder Management | Manage Stakeholder Engagement | Executing |  | Meetings
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 13-7, Page 523.
291 | Stakeholder Management | Monitor Stakeholder Engagement | M&C | Project Management Plan | Data Analysis | Work Performance Information
292 | Stakeholder Management | Monitor Stakeholder Engagement | M&C | Project Documents | Decision Making | Change Requests
293 | Stakeholder Management | Monitor Stakeholder Engagement | M&C | Work Performance Data | Data Representation | Project Management Plan Updates
294 | Stakeholder Management | Monitor Stakeholder Engagement | M&C | Enterprise Environmental Factors | Communication Skills | Project Documents Updates
295 | Stakeholder Management | Monitor Stakeholder Engagement | M&C | Organizational Process Assets | Interpersonal and Team Skills
296 | Stakeholder Management | Monitor Stakeholder Engagement | M&C |  | Meetings
Source -Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Figure 13-9, Page 530.