## Slide 1: Contract Types
PMP Exam Topic

## Slide 2: What is Contract?
A contract is a legally binding agreement between two or more parties that outlines the terms and conditions under which goods, services, or results will be provided. It specifies the rights and obligations of each party.

## Slide 3: Contract and Project Management
Project Charter
Project Requirement
Website
On Page
SEO
Web Development
Off Page
Site
Payment APIs
Outsource
Vendor Contract
Client Contract

## Slide 4: Contract and Project Management
Client Contract (Input to Project Requirements and Charter):
A formal agreement between the client and the organization initiating the project. This contract outlines the project's scope, objectives, deliverables, and the expectations for the final product or service.
Vendor Contract (Executed by Project Team):
A legally binding agreement between your organization and an external vendor or service provider. This contract is used to procure goods, services, or expertise needed for the project that cannot be sourced internally. It specifies the terms of engagement, including scope, cost, timeline, and quality standards.

## Slide 5: Project Manager : Buyer or Seller ?
Client
Project Manager
Vendor
Buyer
Seller
Buyer
Seller
Client Contract
Vendor Contract
Procurement Management

## Slide 6: Contract Types
Contract types are defined by the way costs, risks, and responsibilities are allocated between the buyer and seller in a project. They determine how payment will be made, how project risks are shared, and how changes to the scope or requirements are handled.

## Slide 7: Contract Types
Fixed Price
Cost Reimbursable
Time and Material

## Slide 8: Key Parameters for Contract Type Selection
Clarity of Work
Complexity of Work
Predictability of Estimate or Solution
Degree of Control Needed by Buyer in Contract Execution
Flexibility Needed for Change in Scope
Buyer Cost Control

## Slide 9: Fixed Price

## Slide 10: Fixed Price Contract
A legally binding agreement where the seller agrees to deliver a project or service at a predetermined, fixed cost. The price is set regardless of the actual costs incurred during the project, making it one of the most predictable and stable contract types for buyers.

## Slide 11: Characteristics of Fixed Price Contract Type
Clear Requirements: The project scope, deliverables, and requirements must be well-defined and agreed upon before the contract is signed.
Minimal Scope Changes: Limited flexibility for changes once the contract is in place; any changes typically require a formal change order process.
Fixed Price: The price is predetermined and fixed, providing cost predictability and stability for the buyer.
Risk to Seller: The seller assumes the risk for any cost overruns
Low Buyer Involvement: The buyer has minimal day-to-day involvement.

## Slide 12: Fixed Price: Best Use Cases
Low Complexity Projects: Ideal for projects with low to moderate complexity, where requirements are stable and well-understood.
Government and Commercial Contracts: Commonly used in government and commercial sectors where budget predictability is crucial.
Examples
  Construction Project Contract
  Software Implementation Contract

## Slide 13: Variants of Fixed Price
Firm Fixed Price (FFP): The most common type of contract where the price is set and does not change unless the scope changes. It is favored by buyers because it minimizes surprises and risks.
Fixed Price Incentive Fee (FPIF): Offers a fixed price but includes incentives for the seller based on performance metrics such as cost, schedule, or technical performance.
Fixed Price with Economic Price Adjustment (FP-EPA): Includes a clause for adjusting the price based on economic factors such as inflation or changes in commodity prices, making it suitable for long-term contracts.

## Slide 14: Cost Reimbursable

## Slide 15: Cost Reimbursable Contract
A contract in which the buyer agrees to reimburse the seller for all legitimate and allowable costs incurred during the project. In addition to cost reimbursement, the seller may receive an additional fee, incentive, or award based on performance or achieving specific objectives.

## Slide 16: Characteristics of Cost reimbursable Contract Type
Flexible Scope: Suitable for projects where the scope of work is not well-defined or is expected to change during execution.
Cost Transparency: All costs incurred by the seller are reimbursed by the buyer, including materials, labor, and other expenses.
Buyer’s Control: Regular oversight is required to approve expenses and manage cost.
Risk Allocation: The buyer assumes the majority of the financial risk since all costs are reimbursed.

## Slide 17: Cost Reimbursable : Best Use Cases
High Complexity Projects: Ideal for projects with significant uncertainty, complex requirements, or high levels of risk where the scope cannot be fully defined at the start.
Research and Development (R&D) Projects: Commonly used in R&D, where the outcomes are uncertain, and costs can vary significantly during execution.
High Level of Trust: Requires a high level of trust between the buyer and seller, as the buyer must rely on the seller’s cost reporting and project management practices.

## Slide 18: Variants of Cost Reimbursable
Cost Plus Fixed Fee (CPFF): The seller is reimbursed for all allowable costs and receives a fixed fee as a percentage of the initial estimated cost or sometime actual cost.
Cost Plus Incentive Fee (CPIF): Similar to CPFF, but includes an incentive based on performance, with a cost-sharing formula between the buyer and seller.
Cost Plus Award Fee (CPAF): The seller is reimbursed for all legitimate costs, but the majority of the fee is based on meeting broad and subjective performance criteria.

## Slide 19: Time and Material

## Slide 20: Time and Materials (T&M) Contract
A hybrid contract type that combines elements of both Fixed Price and Cost Reimbursable contracts. In a T&M contract, the buyer pays for the actual time spent and materials used by the seller, with labor billed at an agreed-upon rate and materials billed at cost.

## Slide 21: Characteristics of Time and Material Contract Type
Flexible Scope: Ideal for projects where the full scope of work cannot be defined upfront and may evolve during execution.
Cost Variability: Costs are not fixed; they vary depending on the time spent and materials used.
Buyer’s Control: High level of buyer involvement is needed to manage and approve the time spent and materials used.
Risk Allocation: The buyer assumes the financial risk related to cost overruns due to time or material increases.

## Slide 22: Time and Material: Best Use Cases
Projects with Uncertain Scope: Ideal for projects where the scope is unclear or expected to change, requiring ongoing adjustments.
Agile and Iterative Projects: Well-suited for projects using agile or iterative methodologies, where deliverables and scope evolve over time.
Short-Term or Urgent Projects: Commonly used for short-term projects or tasks that need to start quickly without detailed upfront planning.
Specialized Expertise: Effective for acquiring specialized skills or expertise that are not available in-house, with the flexibility to adjust resource levels as needed.

## Slide 23: Variants of Time and Material
Standard Time and Materials (T&M): The buyer pays for the actual time spent and materials used, with labor billed at pre-agreed rates and materials billed at cost.
Time and Materials with Early Termination Clause: Includes a clause that allows the buyer to terminate the contract early.
Capped Time and Materials: A not-to-exceed limit or cap on the total cost. Once the cap is reached, the buyer is not obligated to pay for additional time or materials.
Time and Materials with Performance Incentives: Combines the T&M model with performance-based incentives.

## Slide 24: Comparison of Contract Types

## Slide 25
Criteria | Fixed Price | Cost Reimbursable | Time and Material
Clarity of Work | High clarity required; scope must be well-defined. | Low clarity; suitable for projects with uncertain scope. | Moderate clarity; flexible to accommodate evolving scope.
Buyer Cost Predictability | High; cost is fixed and predictable. | Low; costs can vary based on actual expenses. | Moderate; labor rates are fixed, but total cost varies with time and materials.
Risk Allocation | Risk is primarily on the seller. | Risk is primarily on the buyer. | Risk is shared; buyer controls costs by managing time and materials.
Engagement Level of Buyer | Low; minimal day-to-day involvement. | High; requires active involvement in cost management. | High; requires active monitoring and approval of time and materials.
Complexity Level | Low to Moderate; best for projects with clear requirements. | High; ideal for complex projects with uncertain scope. | Moderate to High; suitable for projects with evolving scope or specialized expertise.

## Slide 26: Advice for Buyer Project Manager

## Slide 27: Buyer Project Manager : Fixed Price
Define Scope Clearly: Ensure that the project scope, deliverables, and requirements are thoroughly defined and agreed upon upfront to avoid costly change orders.
Minimize Scope Changes: Avoid making changes after the contract is signed, as modifications can lead to additional costs and delays.
Monitor Quality Closely: Even though costs are fixed, maintain oversight to ensure the seller does not cut corners to stay within budget.

## Slide 28: Buyer Project Manage: Cost Reimbursable
Establish Clear Cost Reporting: Set up detailed cost tracking and reporting mechanisms to maintain transparency and control over expenses.
Engage Actively: Be prepared for high involvement in monitoring progress, approving costs, and managing scope changes.
Set Performance Incentives: Consider adding incentives to encourage the seller to control costs and meet performance targets.

## Slide 29: Buyer Project Manager : Time and Material
Fix Labor Rates: Negotiate and agree on labor rates upfront to maintain some control over costs.
Monitor Time and Expenses: Actively track time spent and materials used to prevent budget overruns and ensure project efficiency.
Use Caps or Not-to-Exceed Clauses: Consider setting a cap on total project costs to limit financial exposure and manage budget risks.
Be Flexible with Scope: Leverage the flexibility of T&M contracts to adapt to evolving project needs and requirements.

## Slide 30: Get your Copy of slide : www.izenbridge.com/downloads Video of this session: https://youtu.be/MM3naIlYKls

## Slide 31: Contact Us
www.izenbridge.com
sales@izenbridge.com
+91-9958287711